PROGRESS REPORT

Project Title: Galveston Bay Wetland Mitigation Assessment and Local Government Capacity Building

GLO Contract No: 13-079-000-7102

Reporting Period: 5/01/2014 – 5/31/2014

Task 1:  Assess the long-term status of wetland permit and mitigation sites in the Lower Galveston Bay watershed.

- Status of the task during this reporting period: in progress 	completed

- Briefly describe major accomplishments for this reporting period.

  - Administrative Tasks

    - Monthly Progress Report submitted on 5/10/2014

    - Project Meetings:

      - 5/8/2014: Attendees L. Gonzalez, B. Neish, E. Kinney; Location: HARC

      - 5/13/2014: Attendees L. Gonzalez, E. Kinney, J. Jacob, R. DaVanon; Location: Houston

      - 5/21/2014: Attendees L. Gonzalez, B. Neish, E. Kinney; Location: HARC

      - 5/28/2014: Attendees L. Gonzalez, B. Neish, E. Kinney; Location: HARC

  - Subtask 1: Recruit and convene Advisory Team

    - HARC scheduled the final advisory team meeting on June 25, 2014 from 1:00-3:00 PM at the Galveston Bay Estuary Program (GBEP) offices (17041 El Camino Real, Ste. 210, Houston, Texas 77058). HARC sent the email invitation and has received affirmative RSVPs from 6 stakeholders plus project and GLO staff. See Attachment 1 for email invitation and RSVP list.

    - HARC was scheduled to provide a project presentation at the Galveston Bay Estuary Program Natural Resource Use Subcommittee meeting to be held June 25, 2014 from 9:30-11:30 AM at the GBEP offices. This will elicit additional stakeholder input.

  - Subtask 2: Generate sampling scheme.

    - No additional activity on this task this month; this task is complete.

  - Subtask 3: Document records for chosen quarter quadrangles.

    - See Appendix 1 for full list of records requested and received

    - Received “FOIA M” request (made 4/16/2014) and “FOIA N” request (made 5/5/2014) and “FOIA O” request (made 5/15/2014).

      - Examined all received permits for compliance by comparing full permit record to mitigation bank ledger data available on the USACE RIBITS website and the record made available by the March FOIA

        - 114 of 120 full administrative records received

          - Of those, 105 of 110 total records from random sampling scheme received (90% complete)

        - 6 of 120 requests for full administrative records missing from receipt

      - HARC submitted 2 FOIA requests: “FOIA N” on 5/5/2014 (Please see Attachment 2) for 6 additional full records and “FOIA O” on 5/15/2014 (Please see Attachment 3) for the final 11 full records of the 100 randomly sampled. FOIA O represents the final FOIA request for full permit records and completes this task.

  - Subtask 4: Analyze mitigation in selected CWA Section 404 wetland permit records

    - 102 of 105 permits received have been reviewed.  Dossiers summarizing impacts and completion of each of these permits have been created.  GIS data points for the project location and any known mitigation have been created.  GIS polygons of the project site, impacts, and mitigation sites have been created for each permit.

  - Subtask 5: Verifying 404 permit data and mitigation records

    - This task is complete.

Subtask 6: Determine acreage of existing wetland and mitigation sites in study area

    - Newly acquired permits were added to summary acreage tables for known permits for both March ORM Administrative Record data and data found in full permit administrative records.

    - B. Neish comparing above records to NWI and CCAP land use data

    - List the deliverable(s)/milestone(s) completed during this reporting period.  (Submit a copy of your completed deliverable(s)/milestone(s) with this report.)

    - “FOIA N” on 5/5/2014 (Please see Attachment 2) and “FOIA O” on 5/15/2014 (Please see Attachment 3).

    - Please see Appendix 1 for full list of complete permit records requested and received

- Were there any problems or obstacles encountered during this reporting period (e.g., delays, remedial action taken, schedule revision). Yes 	No  	If yes, please explain:

Briefly describe plans for the next reporting period.

  - Administrative Tasks

    - Monthly Progress Report to be Submitted on 6/10/2014

    - Project Meetings Planned

      - Weekly project meetings:

        - 6/3/2014: Attendees to be L. Gonzalez, B. Neish, E. Kinney; Location: HARC

        - 6/11/2014: Attendees to be L. Gonzalez, B. Neish, E. Kinney; Location: HARC

        - 6/18/2014: Attendees to be L. Gonzalez, B. Neish, E. Kinney; Location: HARC

        - 6/24/2014: Attendees to be L. Gonzalez, B. Neish, E. Kinney; Location: HARC

  - Subtask 1: Recruit and convene Advisory Team

      - Advisory Team meeting planned for June 25, 2014 from 1:00-3:00 PM at the Galveston Bay Estuary Program (GBEP) offices (17041 El Camino Real, Ste. 210, Houston, Texas 77058). Project staff will include Lisa Gonzalez and Erin Kinney from HARC and Rebecca DaVanon from Texas Agrilife.

  - Subtask 2: Generate sampling scheme.

    - Completed

  - Subtask 3: Document records for chosen quarter quadrangles.

    - Complete comparison of ACOE permit/mitigation sites with NWI and CCAP

    - Quantify percentage of wetland mitigation projects that comply with original permit

    - Quantify percentage of wetlands filled with and without permits

  - Subtask 4: Analyze mitigation in selected CWA Section 404 wetland permit records

    - Review final 3 of the 105 permits received.  Complete dossiers summarizing impacts and completion of each of these permits.  GIS data points for the project location and any known mitigation will be created.  GIS polygons of the project site, impacts, and mitigation sites will be created for each permit.

  - Subtask 5: Verify selected mitigation records

    - Completed

  - Subtask 6: Determine acreage of existing wetlands and mitigation sites in study area

    - Brad Neish comparing new 2010 CCAP data to 1995 records

Task 2:  Create a regional decision support tool and training for local governments, allowing them to access information and participate more directly in the wetland conservation, permitting and mitigation in the Lower Galveston Bay watershed.

- Status of the task during this reporting period.  in progress 	completed

- Briefly describe major accomplishments for this reporting period.

  - The decision support tool is currently in an internal Beta phase and has been released for review by a select group of stakeholders.

- List the deliverable(s)/milestone(s) completed during this reporting period.  (Submit a copy of your completed deliverable(s)/milestone(s) with this report.)

  - None at this time

X

Were there any problems or obstacles encountered during this reporting period (e.g., delays, remedial action taken, schedule revision).  Yes 	No  	If yes, please explain:

- Briefly describe plans for the next reporting period.

  - HARC will take feedback on the regional decision support tool from stakeholder workshop and will create final version.

Appendix 1. List of randomly sampled Nationwide and Standard Permits and status of FOIA request

| Agency | GLOMIT FOIA | ACOE FOIA | Date Sent | Date Received | Permit |
| --- | --- | --- | --- | --- | --- |
| TCWP | March/ ORM II FOIA | 13-0157 | 3/24/2013 | 3/28/2013 |  |
| TCWP | June | 13-0207 | 5/29/2013 | 6/17/2013 | SWG-1993-01629 |
| TCWP | June | 13-0207 | 5/29/2013 | 6/17/2013 | SWG-1993-01967 |
| TCWP | June | 13-0207 | 5/29/2013 | 6/17/2013 | SWG-1996-01291 |
| TCWP | June | 13-0207 | 5/29/2013 | 6/17/2013 | SWG-1996-02935 |
| TCWP | June | 13-0207 | 5/29/2013 | 6/17/2013 | SWG-2002-02968 |
| TCWP | June | 13-0207 | 5/29/2013 | 6/17/2013 | SWG-2003-00483 |
| TCWP | June | 13-0207 | 5/29/2013 | 6/17/2013 | SWG-2003-02731 |
| TCWP | June | 13-0207 | 5/29/2013 | 6/17/2013 | SWG-2005-00977 |
| TCWP | June | 13-0207 | 5/29/2013 | 6/17/2013 | SWG-2006-02014-RN |
| TCWP | June | 13-0207 | 5/29/2013 | 6/17/2013 | SWG-2012-00177 |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | 9/16/2013 | SWG-2003-02555 |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | Missing | SWG-2006-00320 |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | 9/16/2013 | SWG-2008-00210-RS |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | 9/16/2013 | SWG-2008-00530 |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | 9/16/2013 | SWG-2008-01178 |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | 9/16/2013 | SWG-2009-00247 |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | 9/16/2013 | SWG-2009-00988 |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | 9/16/2013 | SWG-2009-01124 |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | 9/16/2013 | SWG-2010-01129 |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | 9/16/2013 | SWG-2011-00595 |
| TCWP | August / FOIA A | 13-0272 | 8/21/2013 | 9/16/2013 | SWG-2011-00673 |
| HARC | September/ FOIA B | 13-0300 | 9/18/2013 | 1/10/2014 | SWG-1996-00865 |
| HARC | September/ FOIA B | 13-0300 | 9/18/2013 | 10/16/2013 | SWG-1999-02460 |
| HARC | September/ FOIA B | 13-0300 | 9/18/2013 | 10/16/2013 | SWG-2007-00063 |
| HARC | September/ FOIA B | 13-0300 | 9/18/2013 | 10/16/2013 | SWG-2007-00909-RN |
| HARC | September/ FOIA B | 13-0300 | 9/18/2013 | 10/16/2013 | SWG-2007-01963 |
| HARC | September/ FOIA B | 13-0300 | 9/18/2013 | 10/16/2013 and 1/10/2014 | SWG-2008-00089 |
| HARC | September/ FOIA B | 13-0300 | 9/18/2013 | 10/16/2013 | SWG-2008-00158 |
| HARC | September/ FOIA B | 13-0300 | 9/18/2013 | Missing | SWG-2008-01289 |
| HARC | September/ FOIA B | 13-0300 | 9/18/2013 | 10/16/2013 | SWG-2009-00253 |
| HARC | September/ FOIA B | 13-0300 | 9/18/2013 | 1/10/2014 | SWG-2011-00068 |

| TCWP | ORM II Reports: FY2012 4th Qtr | 14-0010 | 10/1/2013 | 10/23/2013 |  |
| --- | --- | --- | --- | --- | --- |
| HARC | October / FOIA C | 14-0013 | 10/21/2013 | 11/21/2013 | SWG-1995-00699 |
| HARC | October / FOIA C | 14-0013 | 10/21/2013 | 11/21/2013 | SWG-1998-00993 |
| HARC | October / FOIA C | 14-0013 | 10/21/2013 | 11/21/2013 | SWG-1998-01606 |
| HARC | October / FOIA C | 14-0013 | 10/21/2013 | 11/21/2013 | SWG-2002-00852 |
| HARC | October / FOIA C | 14-0013 | 10/21/2013 | 11/21/2013 | SWG-2008-01007 |
| HARC | October / FOIA C | 14-0013 | 10/21/2013 | 11/21/2013 | SWG-2009-00463 |
| HARC | October / FOIA C | 14-0013 | 10/21/2013 | 11/21/2013 | SWG-2009-00671 |
| HARC | October / FOIA C | 14-0013 | 10/21/2013 | Missing | SWG-2011-00489 |
| HARC | October / FOIA C | 14-0013 | 10/21/2013 | 11/21/2013 | SWG-2011-00637 |
| HARC | October / FOIA C | 14-0013 | 10/21/2013 | 11/21/2013 | SWG-2012-00051 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2004-02500 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2006-01851 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2007-00688 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2008-00254-RS |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2008-01144 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2008-01165 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2009-00233 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2009-00842 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2009-01007 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2010-00225 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2010-00402 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2010-00754 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2010-00852 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2011-00734 |
| TCWP | FOIA D | 14-0024 | 11/4/2013 | 12/2/2013 | SWG-2011-01109 |
| HARC | FOIA E | 14-0031 | 11/12/2013 | 12/17/2013 | SWG-1992-02681 |
| HARC | FOIA E | 14-0031 | 11/12/2013 | 12/17/2013 | SWG-1993-00525 |
| HARC | FOIA E | 14-0031 | 11/12/2013 | 12/17/2013 | SWG-1995-00220 |
| HARC | FOIA E | 14-0031 | 11/12/2013 | 12/17/2013 | SWG-1996-01289 |
| HARC | FOIA E | 14-0031 | 11/12/2013 | 12/17/2013 | SWG-1997-00133 |
| HARC | FOIA E | 14-0031 | 11/12/2013 | 12/17/2013 | SWG-2000-02072 |
| HARC | FOIA E | 14-0031 | 11/12/2013 | 12/17/2013 | SWG-2002-01444 |
| HARC | FOIA E | 14-0031 | 11/12/2013 | 12/17/2013 | SWG-2002-01833 |
| HARC | FOIA E | 14-0031 | 11/12/2013 | 12/17/2013 | SWG-2006-00410 |
| HARC | FOIA E | 14-0031 | 11/12/2013 | 12/17/2013 | SWG-2007-00187 |
| HARC | FOIA F | 14-0055 | 12/12/2013 | 1/16/2014 | SWG-1995-01403 |
| HARC | FOIA F | 14-0055 | 12/12/2013 | 1/16/2014 | SWG-1995-01867 |
| HARC | FOIA F | 14-0055 | 12/12/2013 | 1/16/2014/ & ? | SWG-1996-00848 |
| HARC | FOIA F | 14-0055 | 12/12/2013 | 1/16/2014 | SWG-1997-01349 |
| HARC | FOIA F | 14-0055 | 12/12/2013 | 1/16/2014 | SWG-2003-02733 |
| HARC | FOIA F | 14-0055 | 12/12/2013 | 1/16/2014 | SWG-2006-00218 |
| HARC | FOIA G | 14-0063 | 1/2/2014 | 1/17/2014 | SWG-1991-00105 |
| HARC | FOIA G | 14-0063 | 1/2/2014 | 1/17/2014 | SWG-1992-00084 |
| HARC | FOIA G | 14-0063 | 1/2/2014 | 1/17/2014 | SWG-1993-01776 |
| HARC | FOIA G | 14-0063 | 1/2/2014 | 1/17/2014 | SWG-1997-01979 |
| HARC | FOIA G | 14-0063 | 1/2/2014 | 1/17/2014 | SWG-2005-01005 |
| HARC | FOIA G | 14-0063 | 1/2/2014 | 1/17/2014 | SWG-2006-01760 |
| ACOE | ORM II Report: FY2013 4th Qtr PM3 Eligibility Report | No FOIA Request Made | No FOIA Request Made | 1/22/2014 |  |
| TCWP | ORM II Reports: FY2008-2011 4th Qtr |  | 1/16/2014 | 1/27/2014 |  |
| HARC | FOIA H | 14-0074 | 1/16/2014 | 1/31/2012 | SWG-1995-02126 |
| HARC | FOIA H | 14-0074 | 1/16/2014 | 1/31/2012 | SWG-1998-00263 |
| HARC | FOIA H | 14-0074 | 1/16/2014 | 1/31/2012 | SWG-1998-01289 |
| HARC | FOIA H | 14-0074 | 1/16/2014 | 1/31/2012 | SWG-1998-01560 |
| HARC | FOIA H | 14-0074 | 1/16/2014 | 1/31/2012 | SWG-2003-01596 |
| HARC | FOIA H | 14-0074 | 1/16/2014 | 1/31/2012 | SWG-2004-01527 |
| HARC | FOIA I | 14-0081 | 1/23/2014 | 2/14/2014 | SWG-1991-00653 |
| HARC | FOIA I | 14-0081 | 1/23/2014 | 2/10/2014 | SWG-1993-00229 |
| HARC | FOIA I | 14-0081 | 1/23/2014 | 2/14/2014 | SWG-1998-00957 |
| HARC | FOIA I | 14-0081 | 1/23/2014 | 2/10/2014 | SWG-1998-01491 |
| HARC | FOIA I | 14-0081 | 1/23/2014 | 2/10/2014 | SWG-2000-00347 |
| HARC | FOIA I | 14-0081 | 1/23/2014 | 2/10/2014 | SWG-2004-02330 |
| HARC | FOIA J | 14-0116 | 2/20/2014 | 3/13/2014 | SWG-0-19244 |
| HARC | FOIA J | 14-0116 | 2/20/2014 | 3/13/2014 | SWG-1992-01179 |
| HARC | FOIA J | 14-0116 | 2/20/2014 | 3/13/2014 | SWG-1993-00861 |
| HARC | FOIA J | 14-0116 | 2/20/2014 | 3/13/2014 | SWG-1997-01110 |
| HARC | FOIA J | 14-0116 | 2/20/2014 | 3/13/2014 | SWG-2001-00995 |
| HARC | FOIA J | 14-0116 | 2/20/2014 | 3/13/2014 | SWG-2001-02004 |
| HARC | FOIA K | 14-0131 | 3/4/2014 | 4/1/2014 | SWG-1995-00770 |
| HARC | FOIA K | 14-0131 | 3/4/2014 | 4/1/2014 | SWG-1995-01894 |
| HARC | FOIA K | 14-0131 | 3/4/2014 | 4/1/2014 | SWG-1999-01665 |
| HARC | FOIA K | 14-0131 | 3/4/2014 | 4/1/2014 | SWG-2002-01683 |
| HARC | FOIA K | 14-0131 | 3/4/2014 | 4/1/2014 | SWG-2002-01985 |
| HARC | FOIA K | 14-0131 | 3/4/2014 | 4/1/2014 | SWG-2006-00149 |
| HARC | FOIA L | 14-0149 | 4/1/2014 | 4/16/2014 | SWG-1991-00628 |
| HARC | FOIA L | 14-0149 | 4/1/2014 | 4/16/2014 | SWG-1993-00201 |
| HARC | FOIA L | 14-0149 | 4/1/2014 | 4/16/2014 | SWG-1996-02224 |
| HARC | FOIA L | 14-0149 | 4/1/2014 | 4/16/2014 | SWG-2001-00618 |
| HARC | FOIA L | 14-0149 | 4/1/2014 | 4/16/2014 | SWG-2003-02341 |
| HARC | FOIA L | 14-0149 | 4/1/2014 | 4/16/2014 | SWG-2007-00158 |
| HARC | FOIA M | 14-0163 | 4/16/2014 | 5/8/2014 | SWG-1995-00424 |
| HARC | FOIA M | 14-0163 | 4/16/2014 | 5/8/2014 | SWG-1999-01190 |
| HARC | FOIA M | 14-0163 | 4/16/2014 | 5/8/2014 | SWG-2002-01358 |
| HARC | FOIA M | 14-0163 | 4/16/2014 | 5/8/2014 | SWG-2002-01769 |
| HARC | FOIA M | 14-0163 | 4/16/2014 | 5/8/2014 | SWG-2002-02778 |
| HARC | FOIA M | 14-0163 | 4/16/2014 | 5/8/2014 | SWG-2005-02256 |
| HARC | FOIA N | 14-0178 | 5/5/2014 | 5/20/2014 | SWG-1995-00546 |
| HARC | FOIA N | 14-0178 | 5/5/2014 | 5/20/2014 | SWG-1995-01666 |
| HARC | FOIA N | 14-0178 | 5/5/2014 | 5/20/2014 | SWG-1996-00967 |
| HARC | FOIA N | 14-0178 | 5/5/2014 | 5/20/2014 | SWG-1997-01118 |
| HARC | FOIA N | 14-0178 | 5/5/2014 | 5/20/2014 | SWG-1999-00473 |
| HARC | FOIA N | 14-0178 | 5/5/2014 | 5/20/2014 | SWG-2004-02353 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-1992-02684 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-1994-00169 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-1995-00070 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-1995-00406 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-1995-01370 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-1998-01358 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-1998-01995 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-1999-01313 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-2001-01086 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-2004-00790 |
| HARC | FOIA O | 14-0195 | 5/14/2014 | 5/23/2014 | SWG-2005-02367 |

Please provide a current budget breakdown.  (Double Click on budget tables to activate Excel.)

*Obligated includes - funds that have been incurred by the recipient but have not been paid by the recipient, such as executed contract agreements or acquired supplies/materials/equipment.